# DevOps Project Plan: OpenShift CI/CD Platform

Document Version: 1.0   |   Date: February 2026   |   Status: Initial Draft

## Executive Summary

This document provides a comprehensive project plan for establishing a fully automated CI/CD platform on Red Hat OpenShift. Starting from scratch (with the OpenShift cluster already provisioned), the team will implement source control, build pipelines, artifact management, and automated deployment workflows for a multi-tier application stack comprising a React JS frontend, Spring Boot Cloud API layer, and Camunda 8.5 BPM backend.

The project spans 7 months, targeting four sequential environments: DEV → UAT → SIT → PRODUCTION. All pipeline workflows will use GitHub Actions, artifacts will be stored in Sonatype Nexus, and deployments will target OpenShift namespaces per environment.

| Category | Technology | Purpose |
| --- | --- | --- |
| Platform | Red Hat OpenShift | Container orchestration & deployment target |
| VCS | GitHub | Source code version control |
| CI/CD | GitHub Actions | Automated build, test, and deploy pipelines |
| Frontend | React JS | Web application UI |
| API Layer | Spring Boot Cloud | RESTful microservices API |
| BPM/Workflow | Camunda 8.5 | Business process management & workflow automation |
| Artifact Repo | Sonatype Nexus | Docker images, Maven/npm package storage |

# 1. Source Control Repository Strategy

## 1.1 GitHub Organization & Repository Structure

A GitHub Organization will be created to house all repositories. The recommended mono-repo-per-component strategy provides clear separation of concerns while enabling cross-component workflow triggers.

| Repository Name | Type | Contents & Purpose |
| --- | --- | --- |
| org/frontend-reactjs | Application | React JS source code, Dockerfile, env configs, unit tests |
| org/api-springboot | Application | Spring Boot Cloud source, pom.xml, Dockerfile, integration tests |
| org/bpm-camunda | BPM | Camunda 8.5 Helm charts, BPMN files, DMN tables, worker configs |
| org/infra-openshift | Infrastructure | OpenShift manifests, Helm charts, namespace configs, RBAC yamls |
| org/cicd-shared | Shared | Reusable GitHub Actions workflows, composite actions, scripts |
| org/config-repo | Configuration | Environment-specific configs (Spring Cloud Config compatible) |

## 1.2 Branching Strategy

GitFlow-inspired branching strategy with environment promotion gates:

| Branch | Environment | Trigger | Protection Rules |
| --- | --- | --- | --- |
| feature/* | Local / PR | On push – runs lint, unit tests | PR required to merge to develop |
| develop | DEV | On merge – build, push to Nexus, deploy DEV | 1 reviewer, CI must pass |
| release/* | UAT | On branch cut – build, deploy UAT | 2 reviewers, QA sign-off gate |
| release/* | SIT | Manual approval gate – deploy SIT | 2 reviewers + Release Manager |
| main | PRODUCTION | Manual approval gate – deploy PROD | 3 reviewers + CAB approval |

# 2. Service Accounts & Secrets Management

## 2.1 Required Service Accounts

| Service Account | System | Permissions Required | Stored As |
| --- | --- | --- | --- |
| sa-github-actions | GitHub | Repo read/write, Packages, Actions secrets | GitHub PAT (fine-grained) |
| sa-nexus-ci | Sonatype Nexus | Push to docker-hosted, npm-hosted, maven-hosted repos | GitHub Actions Secret: NEXUS_USER / NEXUS_PASS |
| sa-openshift-dev | OpenShift DEV | deploy, get, list, watch in dev namespace | OCP Service Account Token (per-env) |
| sa-openshift-uat | OpenShift UAT | deploy, get, list, watch in uat namespace | OCP Service Account Token (per-env) |
| sa-openshift-sit | OpenShift SIT | deploy, get, list, watch in sit namespace | OCP Service Account Token (per-env) |
| sa-openshift-prod | OpenShift PROD | deploy, get, list, watch in prod namespace (restricted) | OCP Service Account Token (per-env) |
| sa-camunda-deploy | Camunda 8.5 | Deploy BPMN/DMN resources via Zeebe gRPC API | Camunda Client ID + Secret |
| sa-sonar | SonarQube (optional) | Scan projects, publish quality gates | SONAR_TOKEN secret |

## 2.2 GitHub Actions Secrets Structure

Secrets are organized at the GitHub Organization level with environment-scoped overrides:

- Organization Secrets (shared): NEXUS_URL, NEXUS_USER, NEXUS_PASS, SONAR_TOKEN, CAMUNDA_CLIENT_ID, CAMUNDA_CLIENT_SECRET

- Environment Secrets (per-env): OCP_SERVER_URL, OCP_TOKEN, OCP_NAMESPACE

- Repository Secrets (app-specific): APP_specific overrides as needed

Note: Use GitHub Environments (DEV / UAT / SIT / PROD) with required reviewers and deployment protection rules to gate environment secret access.

# 3. CI/CD Pipeline Architecture

## 3.1 Frontend React JS Pipeline

File: .github/workflows/frontend-ci-cd.yml in org/frontend-reactjs

| # | Stage | Tool | Actions |
| --- | --- | --- | --- |
| 1 | Checkout & Setup | actions/checkout | Checkout code, setup Node.js 20 LTS, restore npm cache |
| 2 | Install Dependencies | npm ci | Install exact dependencies from package-lock.json |
| 3 | Lint & Code Quality | ESLint, Prettier | Enforce code standards, fail fast on violations |
| 4 | Unit Tests | Jest, React Testing Library | Run unit tests, generate coverage report (threshold: 80%) |
| 5 | Build | npm run build | Production build with environment-specific .env injection |
| 6 | Containerize | Docker / Podman | Build Docker image with Nginx, tag with git SHA + version |
| 7 | Push to Nexus | docker push | Push image to Nexus Docker hosted repo: nexus/frontend:sha |
| 8 | Deploy to OpenShift | oc / kubectl + Helm | Helm upgrade --install using per-env values.yaml, rolling update strategy |
| 9 | Smoke Test | curl / Playwright | Health check endpoint validation post-deployment |
| 10 | Notify | Slack / Teams | Post build status, image tag, and deployment URL to team channel |

## 3.2 Spring Boot Cloud API Pipeline

File: .github/workflows/api-ci-cd.yml in org/api-springboot

| # | Stage | Tool | Actions |
| --- | --- | --- | --- |
| 1 | Checkout & Setup | actions/checkout | Checkout code, setup Java 21 (Temurin), configure Maven cache |
| 2 | Maven Build & Test | mvn verify | Compile, unit tests, integration tests, code coverage (JaCoCo 80%) |
| 3 | Static Analysis | SonarQube / SpotBugs | Quality gate enforcement, OWASP dependency vulnerability scan |
| 4 | Publish to Nexus | mvn deploy | Push JAR/WAR artifacts to Nexus Maven hosted repository |
| 5 | Containerize | Jib / Docker | Build Docker image (JVM or native), push to Nexus Docker repo |
| 6 | Deploy to OpenShift | Helm | Deploy with ConfigMap injection, env-specific secrets, liveness probes |
| 7 | API Health Check | curl /actuator/health | Validate Spring Boot Actuator health endpoint returns UP |
| 8 | Notify | Slack / Teams | Post deployment summary to team channel |

# 4. Camunda 8.5 OpenShift Setup Pipeline

## 4.1 Camunda Installation Strategy

Camunda 8.5 Self-Managed will be installed via the official Camunda Helm chart into dedicated OpenShift namespaces. The CI/CD pipeline handles Helm-based installation and lifecycle management.

Components installed:

- Zeebe (workflow engine) – stateful set with persistent volumes

- Operate (monitoring UI) – deployment + route

- Tasklist (human task UI) – deployment + route

- Optimize (analytics) – deployment + route (licensed feature)

- Connectors – deployment for pre-built and custom connectors

- Elasticsearch – bundled data store (or external cluster recommended for PROD)

- Identity (Keycloak) – OIDC identity provider for Camunda components

| # | Stage | Tool | Actions |
| --- | --- | --- | --- |
| 1 | Validate Prerequisites | oc CLI | Verify namespace exists, storage classes available, resource quotas set |
| 2 | OpenShift SCC Configuration | oc adm policy | Apply SecurityContextConstraints for Camunda pods (nonroot or custom SCC) |
| 3 | Add Helm Repo | helm repo add | helm repo add camunda https://helm.camunda.io && helm repo update |
| 4 | Create Namespace & Secrets | oc / kubectl | Create namespace camunda-{env}, inject license key, DB passwords, Keycloak secrets |
| 5 | Helm Install / Upgrade | helm upgrade --install | Install camunda/camunda-platform chart with env-specific values-{env}.yaml |
| 6 | Wait for Readiness | kubectl rollout status | Wait for all Camunda pods to reach Running/Ready state (timeout: 15min) |
| 7 | Configure Routes | oc expose / Route YAML | Create OpenShift Routes for Operate, Tasklist, Optimize, Identity UIs |
| 8 | Health Validation | curl + zbctl | Validate Zeebe gateway status, Operate API health, Keycloak realm |
| 9 | Create API Clients | Camunda Identity API | Create M2M client for sa-camunda-deploy, store credentials as GitHub secrets |
| 10 | Notify | Slack / Teams | Post installation summary with component URLs to team channel |

## 4.2 BPMN/DMN Workflow Deployment Pipeline

File: .github/workflows/bpmn-deploy.yml in org/bpm-camunda

This pipeline deploys custom BPMN process definitions, DMN decision tables, and Camunda Forms to the target Camunda cluster using the Zeebe API.

| # | Stage | Tool | Actions |
| --- | --- | --- | --- |
| 1 | Validate BPMN/DMN Files | bpmnlint / xmllint | Lint all .bpmn and .dmn files, validate against BPMN 2.0 schema |
| 2 | Detect Changed Files | git diff | Identify which BPMN/DMN/Form files changed to deploy only deltas |
| 3 | Authenticate to Camunda | Zeebe gRPC / REST | OAuth2 token exchange using CAMUNDA_CLIENT_ID + CAMUNDA_CLIENT_SECRET |
| 4 | Deploy Resources | zbctl / Camunda REST API | zbctl deploy resources *.bpmn *.dmn *.form -- deploy all changed resources |
| 5 | Verify Deployment | Camunda API | Query Operate API to confirm process definitions registered with expected version |
| 6 | Tag Release | gh CLI / git tag | Tag the deployment in git with version and environment label |
| 7 | Notify | Slack / Teams | Post list of deployed process definitions with version numbers |

# 5. OpenShift Environment Configuration

## 5.1 Namespace Structure

| Namespace | Environment | Components | Access |
| --- | --- | --- | --- |
| app-dev | DEV | frontend, api, camunda platform | Dev team full access |
| app-uat | UAT | frontend, api, camunda platform | Dev team deploy-only, QA read |
| app-sit | SIT | frontend, api, camunda platform | Release Manager + DevOps only |
| app-prod | PRODUCTION | frontend, api, camunda platform | CAB-gated, DevOps deploy only |
| nexus | Shared | Sonatype Nexus OSS/Pro | DevOps admin, CI write |
| monitoring | Shared | Prometheus, Grafana, Alertmanager | DevOps admin, team read |

## 5.2 Key OpenShift Configuration Items

- ImagePullSecrets configured in each namespace pointing to Nexus Docker registry

- ResourceQuotas and LimitRanges set per namespace (stricter in PROD)

- NetworkPolicies enforcing namespace isolation with explicit ingress/egress allow rules

- PersistentVolumeClaims for Camunda Zeebe data, Elasticsearch, and Nexus storage

- Horizontal Pod Autoscaler (HPA) configured for frontend and API deployments

- OpenShift Routes with TLS edge termination for all external-facing services

- RBAC: RoleBindings mapping GitHub Actions service accounts to namespace roles

- OpenShift Secrets linked to GitHub Actions environment secrets via External Secrets Operator (recommended) or manual sync

# 6. Sonatype Nexus Repository Configuration

| Repository Name | Type | Format | Purpose |
| --- | --- | --- | --- |
| docker-hosted | Hosted | Docker | Store all built Docker images |
| docker-proxy | Proxy | Docker | Proxy Docker Hub to reduce external pulls |
| docker-group | Group | Docker | Single pull endpoint combining hosted + proxy |
| maven-hosted | Hosted | Maven2 | Spring Boot JARs, internal libraries |
| maven-central-proxy | Proxy | Maven2 | Proxy Maven Central for offline builds |
| maven-group | Group | Maven2 | Combined Maven dependency resolution |
| npm-hosted | Hosted | npm | Internal npm packages |
| npm-proxy | Proxy | npm | Proxy npmjs.com for frontend dependencies |
| helm-hosted | Hosted | Helm | Internal Helm chart repository |

# 7. Project Timeline & Task Breakdown

Total Duration: 7 Months  |  Team: 2-3 DevOps Engineers  |  Start: Month 1

## 7.1 Phase Overview

| Phase | Months | Focus | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1 | M1 – M2 | Foundation & Setup | GitHub Org, repos, Nexus install, OCP namespaces, service accounts, base Helm charts |
| Phase 2 | M2 – M3 | CI Pipelines (DEV) | All 4 CI/CD workflows operational, DEV environment fully automated |
| Phase 3 | M3 – M4 | UAT Promotion | UAT pipeline gates, approval workflows, regression test integration |
| Phase 4 | M4 – M5 | SIT Hardening | SIT pipelines, performance test hooks, security scanning, DR runbooks |
| Phase 5 | M5 – M6 | PROD Readiness | PROD pipeline with CAB gate, rollback automation, monitoring dashboards |
| Phase 6 | M6 – M7 | Go-Live & Handover | PROD go-live, runbook documentation, team knowledge transfer, post-launch support |

## 7.2 Detailed Task Breakdown

### Phase 1: Foundation & Setup (Months 1–2)

| # | Task | Owner | Duration | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 1.1 | Create GitHub Organization, configure SSO/SAML with enterprise IdP | DevOps Lead | 2 days | GitHub Org accessible via SSO, MFA enforced |
| 1.2 | Create all 6 repositories with branch protection rules and .gitignore templates | DevOps Engineer | 2 days | All repos visible, default branch protected, PRs required |
| 1.3 | Install Sonatype Nexus on OpenShift (nexus namespace), configure persistent storage | DevOps Engineer | 3 days | Nexus UI accessible, storage mounted, admin password rotated |
| 1.4 | Configure Nexus repositories (Docker, Maven, npm, Helm) with cleanup policies | DevOps Engineer | 2 days | All repo types operational, CI user can push/pull |
| 1.5 | Create OpenShift namespaces (dev/uat/sit/prod/nexus/monitoring) with ResourceQuotas | DevOps Lead | 2 days | 6 namespaces active, quotas enforced, no default SA leaks |
| 1.6 | Create and configure all service accounts (GitHub SA, Nexus CI SA, OCP SAs per env) | DevOps Lead | 3 days | All SAs created, RBAC applied, secrets stored in GitHub |
| 1.7 | Configure GitHub Organization secrets and Environment secrets per environment | DevOps Engineer | 1 day | Secrets accessible from test workflow, masked in logs |
| 1.8 | Configure OpenShift ImagePullSecrets for Nexus registry in all namespaces | DevOps Engineer | 1 day | Test pod can pull from Nexus Docker registry |
| 1.9 | Create base Helm charts for frontend, API, and Camunda with per-env values files | DevOps Engineer | 5 days | Helm charts lint successfully, values.yaml files for all 4 envs |
| 1.10 | Set up shared GitHub Actions reusable workflows in org/cicd-shared repository | DevOps Lead | 3 days | Reusable workflows callable from any repo in the org |
| 1.11 | Install and configure Camunda 8.5 on DEV namespace via Helm | DevOps Engineer | 4 days | Zeebe, Operate, Tasklist accessible, health checks green |
| 1.12 | Install Prometheus + Grafana in monitoring namespace, configure Camunda & app dashboards | DevOps Engineer | 3 days | Grafana dashboards showing pod metrics, Zeebe metrics visible |

### Phase 2: CI Pipelines – DEV Environment (Months 2–3)

| # | Task | Owner | Duration | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 2.1 | Develop and test Frontend React JS CI pipeline (lint, test, build, containerize, push to Nexus) | DevOps Engineer | 4 days | Pipeline runs end-to-end on develop branch merge |
| 2.2 | Develop and test Spring Boot Cloud API CI pipeline (Maven build, test, Jib containerize, push) | DevOps Engineer | 4 days | Pipeline runs, JaCoCo report published, image in Nexus |
| 2.3 | Develop Camunda installation pipeline for DEV – parameterized Helm install workflow | DevOps Engineer | 3 days | Pipeline can install/upgrade Camunda in DEV on demand |
| 2.4 | Develop BPMN/DMN deployment pipeline with lint validation and zbctl deploy | DevOps Engineer | 3 days | BPMN deployed to DEV Camunda, visible in Operate |
| 2.5 | Configure frontend and API deployment to DEV namespace via Helm (rolling update) | DevOps Engineer | 3 days | Applications reachable via OCP Route in DEV |
| 2.6 | Add smoke test and post-deployment health check steps to all pipelines | DevOps Engineer | 2 days | Pipeline fails and rolls back on failed health check |
| 2.7 | Integrate OWASP Dependency Check and container image vulnerability scanning (Trivy) | DevOps Lead | 2 days | Scan reports published, CRITICAL CVEs fail the pipeline |
| 2.8 | Set up Slack/Teams webhook notifications for pipeline success/failure | DevOps Engineer | 1 day | Team channel receives pipeline outcomes in real-time |
| 2.9 | DEV environment end-to-end integration test: frontend → API → Camunda workflow execution | DevOps Lead + Dev Team | 3 days | Full user journey completes in DEV end-to-end |

### Phase 3: UAT Environment (Months 3–4)

| # | Task | Owner | Duration | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 3.1 | Install Camunda 8.5 on UAT namespace with UAT-specific Helm values (sizing, config) | DevOps Engineer | 2 days | Camunda UAT cluster healthy, separate from DEV |
| 3.2 | Extend all pipelines with UAT stage: add GitHub Environment approval gate (QA sign-off) | DevOps Lead | 3 days | Deployments to UAT require manual approval in GitHub Actions |
| 3.3 | Configure UAT-specific Helm values (resource limits, replica counts, env variables) | DevOps Engineer | 2 days | UAT deployments use correct config, isolated secrets |
| 3.4 | Integrate automated regression test suite execution post-UAT deployment | DevOps + QA Team | 4 days | Test results published to pipeline, failures block promotion |
| 3.5 | Document UAT pipeline runbooks and environment access guide for QA team | DevOps Lead | 2 days | QA team can independently trigger UAT deployments and view logs |

### Phase 4: SIT Environment & Hardening (Months 4–5)

| # | Task | Owner | Duration | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 4.1 | Install Camunda 8.5 on SIT namespace with production-like Helm values | DevOps Engineer | 2 days | Camunda SIT mirrors PROD sizing and config |
| 4.2 | Add SIT stage with dual-approver gate (Release Manager + DevOps) to all pipelines | DevOps Lead | 2 days | SIT deployments require 2 approvals in GitHub Environments |
| 4.3 | Integrate performance/load testing pipeline step (k6 or Gatling) on SIT | DevOps + QA Team | 4 days | Load test reports published, SLO thresholds enforced |
| 4.4 | Implement automated rollback pipeline: on failed deploy, roll back to previous Helm revision | DevOps Lead | 3 days | Pipeline auto-rolls back and notifies team on failure |
| 4.5 | Conduct security hardening review: RBAC, NetworkPolicies, secret rotation, SCC audit | DevOps Lead | 3 days | Security review checklist signed off, no critical findings open |
| 4.6 | Configure Alertmanager rules for Camunda, API, and frontend SLOs | DevOps Engineer | 2 days | Alerts fire to Slack/email on SLO breach in SIT |
| 4.7 | DR simulation: test namespace restore from backup, Camunda state recovery from Elasticsearch snapshot | DevOps Lead | 3 days | DR runbook validated, RTO/RPO objectives met |

### Phase 5: Production Readiness (Months 5–6)

| # | Task | Owner | Duration | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 5.1 | Install Camunda 8.5 on PROD with HA configuration (3x Zeebe brokers, clustered ES) | DevOps Lead | 3 days | PROD Camunda cluster HA, no single point of failure |
| 5.2 | Build PROD deployment pipeline with CAB approval gate and release note requirement | DevOps Lead | 3 days | PROD pipeline waits for CAB-designated approver before proceeding |
| 5.3 | Implement blue-green or canary deployment strategy for frontend and API on PROD | DevOps Lead | 4 days | Zero-downtime deployment verified with traffic splitting |
| 5.4 | Set up backup jobs: Elasticsearch snapshot schedule, Nexus blob store backup, OCP etcd backup | DevOps Engineer | 2 days | Backup jobs scheduled, snapshots verified restorable |
| 5.5 | Complete PROD Grafana dashboards: SLA tracking, Camunda process metrics, business KPIs | DevOps Engineer | 3 days | Dashboards show real-time PROD metrics and historical trends |
| 5.6 | PROD readiness review: pipeline walkthrough, security sign-off, ops runbook review | DevOps Lead + Stakeholders | 2 days | All go/no-go checklist items signed off by stakeholders |

### Phase 6: Go-Live & Handover (Months 6–7)

| # | Task | Owner | Duration | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 6.1 | Execute PROD go-live: deploy all components with CAB approval, monitor for 48hrs | DevOps Lead | 3 days | All PROD components live, no P1/P2 incidents in first 48hrs |
| 6.2 | Write comprehensive pipeline and architecture documentation in Confluence/Wiki | DevOps Lead | 4 days | All pipelines, configs, and runbooks documented and reviewed |
| 6.3 | Conduct hands-on knowledge transfer sessions for ops and development teams | DevOps Lead + Engineers | 3 days | Team can independently trigger pipelines, debug failures, and deploy BPMN |
| 6.4 | Post-launch monitoring, incident response, and pipeline fine-tuning period | DevOps Team | 2 weeks | SLO compliance maintained, on-call runbook validated |
| 6.5 | Project retrospective, lessons learned documentation, and backlog for future improvements | DevOps Lead + PM | 1 day | Retro completed, improvement backlog created and prioritized |

# 8. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Camunda 8.5 SCC compatibility issues on OpenShift | High | High | Pre-validate in DEV early (Month 1), use nonroot SCC template, engage Camunda support |
| GitHub Actions runner hitting OCP API rate limits | Medium | Medium | Deploy self-hosted GitHub Actions runners inside OCP cluster for internal API calls |
| Nexus storage exhaustion blocking CI pipeline artifact pushes | Medium | High | Implement cleanup policies from day 1, set storage alerts at 70% capacity |
| BPMN versioning conflicts during concurrent deployments | Medium | Medium | Use Zeebe resource-based versioning, enforce single deployer service account per env |
| Key team member unavailability during PROD go-live | Low | High | Cross-train at least 2 engineers on all pipeline components, maintain runbooks |
| Environment config drift between SIT and PROD | Medium | High | Use Helm value inheritance, automated config diff check as pre-PROD gate |

# 9. Recommended Team Structure & Tools

## 9.1 Team Roles

| Role | Responsibility | Key Skills Required |
| --- | --- | --- |
| DevOps Lead (x1) | Architecture decisions, OCP RBAC, pipeline design, stakeholder comms | OpenShift, GitHub Actions, Helm, Camunda administration, security |
| DevOps Engineer (x2) | Pipeline development, Nexus config, Camunda Helm, monitoring setup | Docker, Kubernetes/OCP, CI/CD, Nexus, Prometheus/Grafana |
| Dev Team Liaison (x1) | Provide Dockerfiles, assist with app-specific pipeline configs, BPMN testing | React, Spring Boot, Camunda worker development |
| Release Manager (x1) | Coordinate UAT/SIT/PROD gates, CAB submissions, go/no-go decisions | Change management, release coordination, ITIL basics |

## 9.2 Additional Recommended Tooling

- bpmnlint – BPMN file linting in CI pipeline (npm package)

- zbctl – Camunda CLI for Zeebe gateway operations and BPMN deployment

- Trivy – Container image and filesystem vulnerability scanning in CI

- OWASP Dependency Check – Maven plugin for Java dependency CVE scanning

- k6 or Gatling – Load and performance testing integrated into SIT pipeline

- External Secrets Operator – Sync secrets from vault into OpenShift Secrets automatically

- Renovate or Dependabot – Automated dependency update PRs for keeping images current

- GitHub Actions self-hosted runners on OCP – For faster, internal network access to cluster resources